## Student Responsibilities Chart
Student Responsibilities Chart
|  | Student Responsibilities |  | Approximate Timeline*
| Deliverables | Accountable (1 name only) | Responsible (1 or more than 1 name) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
One Time Deliverables and Tasks | Communications Plan | Project Manager | Project Manager | Approximate Timeline* Week 1: DATE COMPLETED
| Business Canvas | Project Manager | Project Manager | bar: Approximate Timeline* Week 2 to Approximate Timeline* Week 3
| Personas | Project Manager | Everyone | bar: Approximate Timeline* Week 3 to Approximate Timeline* Week 4
| Story Map Creation | Scrum Master | Everyone | bar: Approximate Timeline* Week 3 to Approximate Timeline* Week 5
| Entity Relationship Diagram | Scrum Master | Developers | bar: Approximate Timeline* Week 4 to Approximate Timeline* Week 7
| Project Charter | Project Manager | Project Manager | bar: Approximate Timeline* Week 4 to Approximate Timeline* Week 6
| Wireframes | Project Manager | Developers | bar: Approximate Timeline* Week 3 to Approximate Timeline* Week 5
| Business Process Mapping Diagrams | Scrum Master | Scrum Master | bar: Approximate Timeline* Week 3 to Approximate Timeline* Week 4
| Requirements Document | Project Manager | Project Manager | bar: Approximate Timeline* Week 5 to Approximate Timeline* Week 8
| Use Cases | Scrum Master | Scrum Master | bar: Approximate Timeline* Week 5 to Approximate Timeline* Week 15
| Test Cases | Scrum Master | Developers | bar: Approximate Timeline* Week 7 to Approximate Timeline* Week 15
| Test Plan | Scrum Master | Scrum Master | bar: Approximate Timeline* Week 7 to Approximate Timeline* Week 15
| Knowledge Base Population | Scrum Master | Scrum Master | bar: Approximate Timeline* Week 10 to Approximate Timeline* Week 16
| DRP Plan | Project Manager | Project Manager | bar: Approximate Timeline* Week 5 to Approximate Timeline* Week 16
| Transition Plan | Project Manager | Project Manager | bar: Approximate Timeline* Week 14 to Approximate Timeline* Week 16
| User Manual | Project Manager | Project Manager | bar: Approximate Timeline* Week 9 to Approximate Timeline* Week 16
| Technical Manual | Project Manager | Developers | bar: Approximate Timeline* Week 14 to Approximate Timeline* Week 16
| Transition To Client Presentation (Transition to Production/Maintenance) | Project Manager | Everyone | bar: Approximate Timeline* Week 14 to Approximate Timeline* Week 16
| Final Presentation To Students and Instructors | Project Manager | Everyone | bar: Approximate Timeline* Week 14 to Approximate Timeline* Week 16
Ongoing Deliverables and Tasks | Meeting Agenda | Project Manager | Project Manager
| Meeting Minutes | Project Manager | Project Manager
| Meeting Scheduling & Invite | Project Manager | Project Manager
| Sprint Planning Meeting | Scrum Master | Everyone
| Sprint Retrospective Meeting | Scrum Master | Everyone
| Testing (Test Cases) | Scrum Master | Developers
| Ensure Kanban is up to Date (Ralphware) | Scrum Master | Everyone
| Add New Stories to Story Map (Ralphware) | Scrum Master | Everyone
| Work Logs | Project Manager | Everyone
| Preparing with team for Client Meetings | Project Manager | Everyone
| Facilitating Client Meetings | Project Manager | Everyone
| Team Standup | Scrum Master | Everyone
| Team Building | Project Manager | Everyone
| Attendance | Project Manager | Everyone
Legend
Responsible - The person who is in charge of completing the activity.
Accountable - The person who owns the outcome of the activity. (MAXIMUM of 1)
*Please note, these timelines are a guideline as the start/end dates will vary by project. Consult with your instructors to establish projected dates for completion.